## Change Request Log
CR ID | Change Title | Requested By | Description | Impact | Priority | Decision / Status | Owner
CR-001 | Add branch-level performance view | Business / Operations | Add branch dimension and branch-level application, approval and TAT visuals. | Medium | Medium | Approved for analysis design | Business Analyst / BI Team
CR-002 | Add channel performance analysis | Management | Compare branch, web and assisted channels for volume and turnaround. | Low | Medium | Approved | Business Analyst / BI Team
CR-003 | Add pending-age buckets | Loan Operations | Segment pending applications by age to identify ageing cases. | Medium | High | Approved for dashboard design | BA / Operations
CR-004 | Add data-quality exception page | Data / BI | Provide a dedicated page for missing/invalid dates, IDs and required fields. | Medium | High | Approved | BA / BI Team
CR-005 | Change approval-rate denominator | Credit / Risk | Clarify that pending and withdrawn applications are excluded from approval-rate denominator. | High | High | Approved as KPI definition | BA / Credit Manager
CR-006 | Add requested-amount analysis | Finance / Management | Show application volume and average requested amount by loan type and customer segment. | Low | Medium | Approved | BA / BI Team
CR-007 | Add exportable management table | Management | Provide a summarized table suitable for controlled export. | Medium | Medium | Under review | BA / BI Team
CR-008 | Add automated refresh monitoring | Data / BI | Introduce a refresh-status check and visible last-refresh timestamp. | Medium | High | Under review | BI Team

## Impact Assessment
CR ID | Requirements Affected | Process Impact | Data Impact | Dashboard Impact | UAT Impact | Documentation Impact | Recommendation
CR-001 | BR-006, BR-007 / FR-006, FR-008 | Adds branch-level analysis. | Requires branch field. | New branch slicer and visual. | Add branch filter/reconciliation test. | Update BRD/FRD, data dictionary and README. | Proceed after data availability check.
CR-002 | BR-006 / FR-006 | Adds channel comparison. | Uses existing channel field. | Add channel visual/slicer. | Add channel filter test. | Update dashboard specification. | Proceed.
CR-003 | BR-005, BR-007 / FR-005, FR-008 | Improves pending-case monitoring. | Requires valid submission date. | Add pending-age buckets. | Add pending-age validation. | Update KPI/dashboard documentation. | Proceed.
CR-004 | BR-009 / FR-013 | Adds explicit DQ workflow. | Uses validation rules. | New DQ page. | Expand DQ UAT. | Update NFR/DQ documentation. | Proceed.
CR-005 | BR-003 / FR-003 | Changes KPI interpretation. | No new field required. | KPI formula clarification. | Re-execute approval-rate tests. | Baseline KPI definition must be updated. | Proceed with controlled baseline update.
CR-006 | BR-006 / FR-006 | Adds financial segmentation. | Uses requested amount. | New amount visuals. | Add amount reconciliation test. | Update dashboard specification. | Proceed.
CR-007 | BR-007 / FR-008 | Adds controlled output. | Depends on export permissions. | New table/export behavior. | Add export/access test. | Update NFR and user guidance. | Review security before approval.
CR-008 | NFR-001, NFR-003 | Adds operational monitoring. | Requires refresh metadata. | Last-refresh indicator. | Add refresh validation. | Update operating procedure. | Proceed after BI feasibility review.

## Change Workflow
Step | Activity | BA Responsibility | Output
1 | Raise change request | Capture business need, reason and requestor. | Change Request
2 | Initial triage | Clarify scope, urgency and impacted requirements. | Triage decision
3 | Impact assessment | Assess process, data, reporting, UAT and documentation impact. | Impact Assessment
4 | Approval | Present impact, effort and risk to approver. | Decision / Approval
5 | Implement | Update requirements, model, dashboard and documentation as applicable. | Updated artifacts
6 | Validate | Update/execute affected UAT cases and reconcile outputs. | Test evidence
7 | Close | Record final decision, evidence and stakeholder communication. | Closed change record

## Approval Matrix
Change Type | Typical Approver | BA Check
KPI definition change | Credit / Business Owner | Confirm denominator, business meaning and downstream UAT impact.
New dashboard dimension | Business Owner / BI Lead | Confirm source field, usability and performance impact.
Data-quality rule | Data / BI Lead + Business Owner | Confirm false positives, exceptions and remediation.
Security/export change | Business Owner + Security/IT | Confirm access control and data exposure implications.
Major scope change | Project Sponsor | Confirm scope, timeline and priority trade-off.