## UAT Test Cases
Test ID | Requirement | User Story | Scenario | Preconditions | Test Steps | Expected Result | Priority | Status | Actual Result | Defect ID | Tester | Execution Date
UAT-001 | BR-001 / FR-001 | US-001 | Total application count reconciliation | Dataset is loaded | 1. Open dashboard/data model 2. Count application_id records 3. Compare with Total Applications KPI | KPI equals the number of unique application IDs in the source dataset. | High | Not Executed
UAT-002 | BR-002 / FR-002 | US-002 | Monthly application trend and date filtering | Dashboard is available | 1. Select a reporting month 2. Review monthly trend 3. Clear the filter | Trend updates to the selected period and returns to the full reporting period when cleared. | High | Not Executed
UAT-003 | BR-003 / FR-003 | US-003 | Approval rate calculation | Approved and rejected records exist | 1. Record Approved count 2. Record Rejected count 3. Calculate Approved/(Approved+Rejected) 4. Compare with KPI | Approval Rate uses only eligible decided applications as the denominator and matches the calculated value. | High | Not Executed
UAT-004 | BR-004 / FR-004 | US-004 | Turnaround time calculation | Valid submission and decision dates exist | 1. Select completed applications 2. Compare processing days with decision date minus submission date 3. Review average/median TAT | Processing days and summary measures follow the documented turnaround-time definition. | High | Not Executed
UAT-005 | BR-005 / FR-005 | US-005 | Stage bottleneck visibility | Stage/application_stage data is available | 1. Open Operations page 2. Compare processing days by stage 3. Identify high-processing stages | Stage-level processing metrics are displayed and can be compared without calculation errors. | Medium | Not Executed
UAT-006 | BR-006 / FR-006 | US-006 | Loan type and region filters | Dashboard contains loan type and region slicers | 1. Select a loan type 2. Select a region 3. Review KPI/cards/charts | All applicable visuals and KPIs update consistently to the selected loan type and region. | High | Not Executed
UAT-007 | BR-006 / FR-007 | US-007 | Customer segment analysis | Customer segment data is available | 1. Open Credit & Customer page 2. Select a customer segment 3. Compare approval and application metrics | Customer-segment metrics reflect the selected segment and reconcile to source data. | Medium | Not Executed
UAT-008 | BR-007 / FR-008 | US-008 | Executive dashboard KPI visibility | Executive Overview page is published | 1. Open page 2. Verify KPI cards 3. Review trend and distribution visuals | Required executive KPIs and core visuals are visible, readable, and aligned with requirements. | High | Not Executed
UAT-009 | BR-008 / FR-009 | US-009 | KPI definition and reconciliation | KPI definitions are documented | 1. Review KPI definitions 2. Independently calculate selected KPIs 3. Compare dashboard results | Dashboard calculations match the approved KPI definitions and independently calculated values. | High | Not Executed
UAT-010 | BR-009 / FR-013 | US-010 | Data-quality exception validation | Data-quality rules are configured | 1. Review missing/invalid dates and required fields 2. Compare exception count with DQ measure/report | Known data-quality exceptions are flagged and do not silently distort KPI calculations. | High | Not Executed
UAT-011 | BR-010 / FR-015 | US-011 | Requirements traceability validation | RTM is available | 1. Select representative BRD requirements 2. Trace to FRD, user story and UAT ID | Each in-scope requirement has a traceable path through FRD/user story/UAT coverage. | High | Not Executed
UAT-012 | FR-014 | US-012 | Dashboard drilldown | Drilldown-enabled visual is configured | 1. Select a summary visual 2. Drill into detail 3. Return to summary | Drilldown provides the intended detail and preserves filter context. | Medium | Not Executed
UAT-013 | BR-003 / FR-003 | US-003 | Pending application analysis | Pending records exist | 1. Filter status to Pending 2. Review count and rate 3. Compare with source | Pending applications are shown separately and are not included in the approval-rate denominator. | High | Not Executed
UAT-014 | NFR-002 | US-008 | Access and security validation | Test user access is provisioned | 1. Log in as authorized user 2. Verify dashboard access 3. Verify unauthorized access is blocked | Only authorized users can access the analytical dashboard and underlying data. | High | Not Executed
UAT-015 | NFR-001 / NFR-003 | US-008 | Reporting period and refresh validation | Refresh process is configured | 1. Refresh dataset 2. Confirm latest reporting period 3. Check for refresh/data-quality errors | Refresh completes successfully and the dashboard reflects the intended reporting period. | Medium | Not Executed

## RTM Validation
BRD ID | FRD ID | User Story | UAT ID | Coverage Status
BR-001 | FR-001 | US-001 | UAT-001 | Covered
BR-002 | FR-002 | US-002 | UAT-002 | Covered
BR-003 | FR-003 | US-003 | UAT-003 / UAT-013 | Covered
BR-004 | FR-004 | US-004 | UAT-004 | Covered
BR-005 | FR-005 | US-005 | UAT-005 | Covered
BR-006 | FR-006 / FR-007 | US-006 / US-007 | UAT-006 / UAT-007 | Covered
BR-007 | FR-008 | US-008 | UAT-008 | Covered
BR-008 | FR-009 | US-009 | UAT-009 | Covered
BR-009 | FR-013 | US-010 | UAT-010 | Covered
BR-010 | FR-015 | US-011 | UAT-011 | Covered

## UAT Summary
Metric | Value
Total test cases | 15
High priority | 10
Medium priority | 5
Executed | 0
Passed | 0
Failed | 0
Blocked | 0
Not Executed | 15
Note | Execution results are intentionally blank/not executed for this portfolio artifact.

## Defect Log
Defect ID | UAT ID | Description | Severity | Priority | Status | Assigned To | Target Date | Resolution