## Stakeholder Register
Stakeholder ID | Stakeholder | Role | Power | Interest | Impact | Key Needs | Engagement Approach | Communication Frequency
SH-001 | Project Sponsor | Business Sponsor | High | High | High | Business outcomes, progress, risks, decisions | Steering review and decision meetings | Bi-weekly
SH-002 | Loan Operations Manager | Process Owner | High | High | High | Turnaround time, bottlenecks, workload visibility | Process workshops and KPI reviews | Weekly
SH-003 | Credit Manager | Credit Process Owner | High | High | High | Approval/rejection analysis, process controls | Requirements workshops and validation | Weekly
SH-004 | Finance Manager | KPI / Finance Owner | High | Medium | High | Consistent KPI definitions and reconciliation | KPI definition and review sessions | Bi-weekly
SH-005 | Risk & Compliance | Control Owner | High | Medium | High | Governance, data controls, auditability | Requirement and control reviews | At key gates
SH-006 | Branch / Sales Teams | Business Users | Medium | High | Medium | Application visibility and status reporting | User interviews and demos | Weekly
SH-007 | Data / BI Team | Technical Team | Medium | High | High | Clear data definitions, logic and dashboard requirements | Technical walkthroughs | Weekly
SH-008 | Business Analyst | BA / Product Analyst | Medium | High | High | Traceability, stakeholder alignment and acceptance | Facilitation, documentation and follow-up | Ongoing

## RACI Matrix
Deliverable / Activity | Sponsor | Operations | Credit | Finance | Risk | Sales | Data/BI | BA
Project Charter | A | C | C | C | C | C | C | R
Stakeholder Analysis | A | C | C | C | C | C | C | R
BRD | A | C | C | C | C | C | C | R
FRD / KPI Specification | C | C | R | C | C | C | R | A
AS-IS / TO-BE Process | A | R | R | C | C | C | C | A
User Stories | C | C | C | C | C | R | C | A
Data Analysis / SQL | C | C | C | C | C | C | R | A
Power BI Dashboard | C | C | C | C | C | C | R | A
UAT | A | R | R | C | C | R | C | A
Change Management | A | C | C | C | C | C | C | R
Final Recommendations | A | C | C | C | C | C | C | R

## Elicitation Questions
Area | Question
Business Goal | What business outcomes should the loan analytics solution support?
Process | Which stages create the greatest delay in the loan application lifecycle?
KPI | How does the business currently define approval rate and rejection rate?
KPI | Which turnaround-time definition should management use?
Data | Which application fields are mandatory for reporting?
Segmentation | Which loan types, regions and customer segments require analysis?
Dashboard | Which KPIs must appear on the executive dashboard?
Security | Who should be allowed to view application-level or aggregated information?
UAT | What evidence would make business users accept the solution?
Change | Who can approve changes to approved requirements?